## Sheet1
Nontidal Network Project Water Year XXXX Data Life Cycle Process with Activity Timelines
Calendar Year XXXX-1 | [11 empty] | Calendar Year XXXX | [11 empty] | Calendar Year XXXX+1 | [12 empty] | Calendar XXXX+2
Latter Part of WYXXXX-1 | [8 empty] | Water Year XXXX | [11 empty] | Water Year XXXX+1 | [12 empty] | Water Year XXXX+2 | [11 empty] | Water Year XXXX+3
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar |  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Latter Part of WYXXXX-1 Jan: NTNP staff (Project Coordinator, Data Manager, Quality Assurance Coordinator) meet with NTNP Data Providers and Data Collectors discuss most recently completed Data Life Cylce (WYXXX-2) (see WY2012 NTN DUET Summary Data Review Tables Aug 20 2012)…utilize above to revise NTN Guidance, QAPPS, Grants, ...for WYXXX+2; Latter Part of WYXXXX-1 May: Data Collectors: Update and submit revised Xcell spreadsheets from WYXXX-1 and submit to NTNP Data Manger (DM). (1) Expected (M1, S1) WQP and related metadata (see Xcell Worksheet NTN FAST_DUET_ESAR Expected WQ and Meta Data WY2012) also use in QAPP (2) Analytical Lab and method information (see TAB_METHOD_MDL_PQL 1 MDDNR_Aug 22 2012) also use in QAPP (3) POC information (see Master POC Info_NTN_ESAR POC STD EX000019.2_Labs_June 13 2012); Water Year XXXX Oct: Data Collectors begin to collect WY XXXX expected water quality, quality control, and related ancillary metadata; Water Year XXXX+1 Oct: Data Collectors begin to collect WYXXXX+1 expected water quality, quality control, and related ancillary metadata | [7 empty] | Data Collectors begin to collect WYXXXX+2 expected water quality, quality control, and related ancillary metadata
|  |  |  | NTN DM Identifies WQPs to be calculated given expected WQP from each Data Collector, revises expected and calcualted WQPs for FS1 and FS2 and FB samples, modifies all DUET Summary Tables as needs be). Passes above to DUET Programmers. | [5 empty] | Data Collectors compile, review, and prepares expected water quality, quality control, and metadata for submission
|  |  |  | DUET programmers revise DUET to process data for coming WY | [7 empty] | Data Collectors submit expected WY XXXX Data to their Data Provider within this time period..recommend intial new data uploads before March 1st; and revised data uploads before Mar 15th st; in MS Access Format
Water Year XXXX Jan: Data Provider uploads WY XXXX Data Using DUET within this time period; initial new data uploads no later than March 15th; revised data uploads no later than March 31st; Water Year XXXX+1 Mar: 15th | 31st
Water Year XXXX Jan: DUET evaluates and produces interim reports on timeliness, completeness, and quality of data uploaded into WQ_1 and metadata databases, which are sent to Data Providers and Collectors |  | DUET produces summary reports on timeliness, completeness, and quality of data uploaded into WQ_1 and metadata databases
[28 empty] | NTN DM transforms data for use by USGS to determine trends and loads; provides summary reports on quality of data | USGS Obtains data and analyzes for Loads and Trends | USGS reports out initial Loads and Trends results | USGS formally reports out initial Loads and Trends results
[28 empty] | NTN Staff (PC, DM, QAC) provide and discuss summary reports with NTN Data Providers and Collectors with eye towards modifications to WYXXXX+2 data collection and submission. |  |  | NTNP Staff (PC, DM and QAC) discuss utlity of generated NTNP database for USGS use to improve future transformation of data for use
NTNP Staff (PC, DM and QAC) post final text and summary tables describing WT data in ESAR Subelements for WYXXXX
[31 empty] | NTNP DM and IT finalize WYXXXX (WQ and METADATA) and publish in accordance with ESAR standards |  |  |  | These WQ and METADATA databases will be recommended for use by CBP Data Modelers (2017), as well as CBP partners, and general public; as they have the benfit of potentially being further qualified on basis of the USGS interpretation of WYXXX data
NTN PC reviews and closes out Data Life Cycle in accordance with ESAR Project final results for WYXXXX