## Sheet1
ID | Date | POC | Description | Due Date | Status
0 | 2010-09-27 | Jezek | last bullet of Terms of Reference Slide | 2010-10-15 | DONE
1 | 2010-09-27 | Wagner/Jezek/Menge | communicate science team and operating venue expectations to the community. | 2010-12-15 | Plan to do this at AGU townhall: DONE
2 | 2010-09-27 | Jezek/Menge | talk to NSIDC about data products (e.g. production of sea ice thickness products). Provide NSIDC with recommendations on data products while recognizing that data products are ‘not our job’! Link to NSIDC Wiki on IST web page. | 2010-10-15 | Telcon with NSIDC on Sept 30. Followup planned. No public Wiki yet available - DONE
3 | 2010-09-27 | Luthcke | send team a recommendation on how GRACE can be improved by incorporating IceBridge data. | 2010-10-15 | Done - integrating data sets in progress
4 | 2010-09-27 | All | Team members with cal val interests need to volunteer to develop instrument intercomparison plan | 2010-10-15 | Suggestion for working group: Luthcke, Farrell, Smith, Csatho, Young. Superceded by instrument summit in June 2011
5 | 2010-09-27 | Young | ICECAP flight line plans to the team | 2010-10-15 | Done and good continuing interaction
6 | 2010-09-27 | Fahnestock | needs flight lines from each OIB team component. He can then provide coordinates in tables. Mark is accumulating information on where data are acquired. This task is done. M. Fahnestock needs to implement a similar capability for Greenland. | 2010-12-01 | DONE
7 | 2010-09-27 | E. Rignot, I. Joughin, R. Kwok | draft a recommendation from the IST to the Project and Program on access to InSAR data | 2010-12-01 | Jezek has followed up with CSA and DLR. Letter sent
8 | 2010-09-27 | McAdoo | provide a link between NOAA and IceBridge planning and implementation. | 2011-01-20 | Update at January meeting requested
9 | 2010-09-27 | Joughin | Overview/status presentation on picking errors on Snow Accumulation radar from I. Joughin’s team. | 2010-01-20 | Process is not mature enough yet for a briefing
10 | 2010-09-27 | Csatho, Farrell, Kwok, Smith | Go through ICESat 2 science requirements and track to OIB reqs | 2010-10-31 | DONE: I2 requirments provided by Markus and reviewed
11 | 2010-09-28 | Martin | Send out January Meeting details and invite international guests | 2010-10-01 | DONE
12 | 2010-09-28 | Jezek | post schedule of science team deliverables | 2010-10-15 | DONE: posted on web site
13 | 2010-09-28 | Richter-Menge | Appoint 3 or 4 team members to take the lead on sensor intercomparison plan and giving a presentation at the January meeting. | 2010-10-31 | Suggestion for working group: Luthcke, Farrell, Smith, Csatho, Young. Develop a plan for ICESat/OIB/Cryosat/ICESAt2 continuity and sensor intercomparison. See 4
14 | 2010-09-28 | Studinger, Koenig | Draft a generic OIB acknowledgement for posting on NSIDC data web site | 2010-10-31 | Also encourage people to cite EOS paper in publications
15 | 2010-09-28 | Fahnestock | to have both Greenland and Antartica information on line by time of AGU town hall meeting | 2010-12-01 | Done: available for use during flight planning
16 | 2010-09-28 | Wagner, Studinger | determine whether elevation data need to be provided referenced to a common datum or whether each investigator is responsible for doing the transformations. | 2010-12-01 | Addresses the general issue of the level of advice (If any) that the Science Team will provide to NSIDC and the SWG. Done SWG is separte activity
17 | 2010-09-29 | Jezek | Organize Level 1 requirements telecon | 2010-10-29 | DONE
18 | 2010-09-29 | Jezek, Richter Menge | Provide draft, science team consenus Level 1 requirements to project | 2010-11-15 | DONE
19 | 2010-09-29 | Jezek | Organize bi-weekly telecons for Greenland Planning | 2010-10-15 | DONE
20 | 2010-09-29 | All | Draft of Greenland flight plans | 2010-01-21 | Done
21 | 2011-10-29 | Jezek | Revise list of OIB program goals | 2011-11-01 | Done
22 | 2011-10-29 | Luthcke | Draft 4th bullet to add science team responsibility for data quality control | 2011-11-01 | DONE: but check to be sure it is in the document
23 | 2011-10-29 | Rignot | Identify a list of achievable requirements | 2011-11-01 | Done: superceded by redraft of document
24 | 2011-10-29 | Joughn | Turn science objectives from questions to statements | 2011-11-01 | Done: superceded by redrafts
25 | 2011-10-29 | Fahnestock, Luthcke, Csatho | add comments about icebridge connection to Grace to science doc | 2011-11-01 | Done
26 | 2011-10-29 | Csath and Farrell | Turn question in section 3 of draft report into statements | 2011-11-01 | Done: superceded by redrafts
27 | 2011-10-29 | Richter-Menge | Check that sea ice is represented in Program/Project documentation | 2011-11-01 | Done
28 | 2011-10-29 | Csatho | Provide a map of elevation change for assessing sampling | 2011-11-01 | Done
29 | 2011-10-29 | Bell | Provide a map illustrating gravity sampling | 2011-11-01 | Done
30 | 2011-10-29 | Smith | Inform the OIB team if ICESat-2 Science team activiting regarding surface sampling strategies can be applied to OIB flight planning decisions | 2011-01-19 | Csatho has inquired about SDT assistance to OIBST. Will followup in June
31 | 2011-10-29 | Jezek | send a lis tof high level science bullets that flow into requirements | 2011-11-01 | Done
32 | 2011-11-10 | Bell | Draft additional requirements on gravity and basal boundary condition | 2011-11-15 | Done: requirements added but awaiting paragraph of justification
33 | 2011-11-10 | Csatho | Provide requirements on optical photography | 2011-11-14 | Done: requirements added but awaiting paragraph of justification
34 | 2011-11-10 | Jezek | assure measurement consistency is integrated in project documents | 2011-01-19 | Ongoing
35 | 2011-11-10 | Csatho | Confirm accuracy of glaciers and ice caps requirements with other colleagues | 2011-11-15 | done
36 | 2011-11-10 | McAdoo | Add requirements for gravity over sea ice | 2011-11-15 | Done
37 | 2011-01-10 | Sonntag | Draft plans assuming P3 basing at Thule/Fairbanks | 2011-01-19 | Done
38 | 2011-01-10 | Sea ice team | develop contingency flights out of fairbanks | 2011-01-19 | Done
39 | 2011-01-10 | Richter-Menge | Investigate coordination with SCICEX | 2011-01-19 | Done
40 | 2011-01-10 | Lindsay | Provide coordinates on Beufort moorings | 2011-01-19 | Done
41 | 2011-01-10 | Sonntag | Redraw Fram Strait Flight line for less ice condition | 2011-01-19 | Done
42 | 2011-01-10 | Sea ice team | shorten zig zags and prioritize | 2011-01-19 | Done
43 | 2011-01-10 | McAdoo | update information on Envisat tracks | 2011-01-19 | Done
44 | 2011-01-10 | Sea ice team | optimize coordination with CryoVex | 2011-01-19 | Done
45 | 2011-01-12 | Sea ice team | finish requirements jusfications with attention to SI1 and SI2 | 2011-01-19 | Done
46 | 2011-01-12 | Land Ice Team | finish requirements jusfications with attention to IS4, IS9, IS13, IS14, IS15, P2, P4, P5, P6, P7 | 2011-01-19 | Done
47 | 2011-01-12 | All | Data assessment report to Project | 2011-10-31 | Done
48 | 2011-01-12 | All | End to end icebridge strategy and schedule | 2011-12-31 | Done
49 | 2011-01-13 | Fahnestock | Investigate whether proposed ridge/borehole flight complements IceBridge | 2011-01-19 | Done
50 | 2011-01-13 | Luthcke | Refine cryocore flight line to optimize ICEsat repeat coverage | 2011-01-19 | Done
51 | 2011-01-13 | Csatho | way points for a southeast Greenland flight in vicinity of Narsarsuaq | 2011-01-19 | Done
52 | 2011-01-20 | Studinger | Data policy for Cryovex agreement | 2011-02-15 | Done
53 | 2011-01-20 | Kaminski | Update data status chart | 2011-02-01 | Done
54 | 2011-01-20 | Sonntag | Fly same EGIG coordinates as Forsberg | 2011-02-01 | Done
55 | 2011-01-21 | Young | Coordinate IceBridge Icecap flight planning | 2011-02-15 | Done
56 | 2011-01-21 | Luthcke | Draft a flight line data sampling strategy | 2011-03-15 | Done
57 | 2011-01-21 | All | Schedule telecons and next meeting | 2011-02-15 | Done
58 | 2011-05-18 | All | Draft Antarctic Flight Lines | 2011-06-18 | Done
59 | 2011-05-18 | All | Finalize June Meeting agenda | 2011-06-13 | Done
60 | 2011-05-25 | Ice Sheet Team | Review IS7 | 2011-06-18 | Done
61 | 2011-05-25 | All | Submit science vu-graphs to project for Wagner Review | 2011-06-18 | Done
62 | 2011-05-25 | Larour/Nowicki | Assemble flight line recommendations from the modeling team | 2011-06-13 | Done
63 | 2011-05-25 | Joughin | Detailed recommendations on Bindschadler request | 2011-06-13 | Done
64 | 2012-06-16 | All | Assess seasonal/spatial and platform requirements for long term OIB strategy | Spring meeting | Done
65 | 2012-06-16 | All | move basal water layer detection from a research to operational product | Spring meeting | Done - requirement changed to indicate radar practicality (3 dB)
| 2012-06-16 | Paden | McCords error statistics | Spring meeting | Done - Jezek provided cross over analysis
| 2012-06-16 | Paden | Request to provide KU with format feedback | 2012-07-31 | Done - iterations still occuring given subsequent feedback from NASA HQ
| 2012-06-17 | Larour/Nowicki/Csatho | Prototype data stream to take OIB from raw data to model products | Spring meeting | in progress
| 2012-06-17 | Sonntag/Young | GPS processing teams to assist UT team to resolve altimeter error issue | 2012-08-31 | in progress
| 2012-06-17 | All | prioritize antarctic flight lines | 2012-09-30 | Done
| 2012-01-27 | all | Finalize all Arctic 2012 flights | 2012-02-27
| 2012-01-27 | smith, Sonntag | provide colored priorization and repeat coverage maps to project | 2012-02-27
| 2012-01-27 | NSIDC | Work with instrument teams to produce zeroth order product definition documents | Summer meeting
| 2012-01-27 | all | Develop a strategy for assessing utility of Cryosat underflihts | Summer meeting
| 2012-01-27 | Hofton | Provide colored prioritization map for Falcon to Project