CLIMATE CHANGE AND HEALTH PLAN

Department of Health

Government of Niue

April, 2012

Acknowledgements

This Climate Change and Health Plan is the result of an extensive and ongoing collaboration between the Niue Department of Health (DoH) and the World Health Organization (WHO) - coordinated by the WHO Western Pacific Regional Office (Manila, Philippines) and facilitated by the WHO Division of Pacific Technical Support (Suva, Fiji) with expert input from a team of academics from the University of Auckland, New Zealand and funding from the Government of Korea (Ministry of Environment, Korea Foundation for International Healthcare and Korea Centres for Disease Control and Prevention) and the Government of Japan (Japan Voluntary Contribution).  The contributions from stakeholders from a range of Niue government departments and communities are also gratefully acknowledged.

Index

List of abbreviations									4

1.  Introduction									5

2.  Overview of the climate change and health vulnerability and adaptation assessment process									7

3.  Climate change in Niue								8

4.  Climate-sensitive health risks and adaptation options				8

4.1  Vector-borne diseases					10

4.2  Ciguatera							11

4.3  Diarrhoeal disease						12

4.4  Respiratory disease					13

4.5  Heat-related illness						14

4.6  Non-communicable diseases				15

4.7  Health impacts of extreme weather events		16

4.8  Skin infections/infestations				17

5.  Findings and conclusions								18

6.  Recommendations								19

References										21

Appendix										22

Table 1.  Key climate-sensitive health issues discussed in Phase One			22

Table 2.  Phase One plan for CC&H activities						23

Table 3.  Main health issues in Niue identified in Phase Two stakeholder meeting	23

Table 4.  List of key points from Phase Two community consultations			24

List of abbreviations

CC&H		climate change and health

DAFF		Department of Agriculture, Fisheries and Forestry

DMCC		Department of Meteorology and Climate Change

DoE		Department of Environment

DoH		Department of Health

ENSO		El Niño Southern Oscillation

HIS		Health Information Systems

JNAP	Joint National Action Plan on Climate Change and Disaster Risk Management

IWRM		Integrated Water Resource Management

NCCP		National Climate Change Policy

NCD		non-communicable disease

NHSP		National Health Strategic Plan

PACC		Pacific Adaptation to Climate Change

PCCSP		Pacific Climate Change Science Program

UNFCCC	United Nations Framework Convention on Climate Change

WHO		World Health Organization

1.  Introduction

As one of the smallest countries in the Pacific region, Niue is among a unique group considered to be significantly vulnerable to the effects of climate change.  These effects include impacts on health that are likely to be detrimental in the absence of appropriate coping strategies (otherwise known as “adaptations”).

The health impacts of climate change were considered in Niue’s Initial National Communication to the United Nations Framework Convention on Climate Change (UNFCCC) in 2000.  This important document listed the key health risks from climate change as they were perceived at that time, including mosquito-borne diseases (such as dengue fever and lymphatic filariasis), diarrhoeal and respiratory illnesses, ciguatera (fish poisoning) and the health impacts of extreme weather events such as cyclones and droughts.

Since that time, Niue has developed a National Climate Change Policy (NCCP, 2009), which identified health as a vulnerable sector (along with water, energy, infrastructure, tourism, natural ecosystems, fisheries, forestry and agriculture).  The NCCP also calls for the development and implementation of appropriate adaptations to reduce vulnerabilities in each sector.  Implementation of the NCCP is to be guided by the Joint National Action Plan for Climate Change and Disaster Risk Management (JNAP), which is currently being drafted.

Climate change issues have also been considered in the National Health Strategic Plan (NHSP, 2011-2021), in which it is recommended that a “health-sector specific” plan for climate change and disaster preparedness and response be developed.

This Climate Change and Health (CC&H) Plan for Niue is the health sector’s response to the recommendations made in both the NCCP and NHSP.  It also acknowledges the commitments made by the Pacific Health Ministers to tackle climate change and health issues at their biennial meeting in Madang, Papua New Guinea in 2009.  It is intended that this CC&H Plan feed back into the JNAP, and that the issues and adaptation options outlined in this Plan be referenced in Niue’s subsequent communications to the UNFCCC (the Second National Communication is currently in final draft form) and be included in future DoH workplans and policies.

The links between this CC&H Plan and the other high-level policies and frameworks that guide health and climate change planning in Niue are represented in Figure 1 below.

Figure 1.  Links between climate change policies and plans related to health in Niue

NHSP

NHSP

NCCP

NCCP

CC&H Plan

CC&H Plan

JNAP

JNAP

This CC&H Plan lays out Niue’s key health vulnerabilities in the context of climate change, assessed on the basis of the latest climate change science, an understanding of the current burden of climate-sensitive diseases (CSD’s) in Niue and the likely impact of climate change on these health issues.

This document includes an overview of the CC&H vulnerability and adaptation assessment process used by the DoH-WHO team over the course of this CC&H planning project in Niue, a summary of the main climate change phenomena expected in Niue, a brief description of the burden of CSD’s in Niue, a list of suggested strategies and activities to manage future climate change-attributable burden of disease (based on stakeholder consultations and expert advice) and some recommendations on how to proceed in implementing this Plan.

Fundamentally, it is intended that this CC&H Plan document be used to prioritize the activities of the health sector in relation to those health issues thought to be sensitive to changes in climate, in order to avoid the most serious impacts of climate change on the health of individuals and communities in Niue.

2.  Overview of the climate change and health vulnerability and adaptation assessment process

This project was conducted in three phases between 2010 and 2012.

Phase One:

In July 2010 a WHO-sponsored workshop on climate change and health for five Pacific countries (Cook Islands, Kiribati, Niue Tonga and Tuvalu) was hosted by the University of Auckland.  The aims and objectives of the workshop were to identify the key current and emergent climate change health vulnerabilities for each country.  Niue sent a team of five representing four government departments: DoH, Department of Environment (DoE), Niue Department of Meteorology and Climate Change (NMCC) and the Department of Agriculture, Fisheries and Forestry (DAFF).  The key CC&H priorities identified for Niue in Phase One are listed in Table 1 in the Appendix.

An emphasis by the Niue team was of the need for health data on priority conditions to be collated along with local climate data.

Based on these discussions a plan of action was outlined by the Niue team for subsequent phases of the project (Table 2 in the Appendix).

Phase Two:

In March 2011, a visit to Niue by Dr Teuila Percival and Dr Vili Nosa (University of Auckland) was undertaken to engage with the Niue CC&H team and follow up on the key climate health change developments since the 2010 workshop in Auckland. This visit also involved key stakeholder interviews with Niue Police Health, Niue Public health department, Nurses’ division and community health.

The key points raised in the meetings with stakeholders and consultation with communities during this country visit are listed in Tables 3 and 4 in the Appendix.

Phase Three:

The final phase for this project involved a return visit to Niue in April 2012 by Dr Vili Nosa (University of Auckland) and Dr Lachlan McIver (Climate Change and Health Officer, WHO Division of Pacific Technical Support).  The aim of this visit was to assist the CC&H team in Niue to complete the CC&H Plan for Niue.  Key informant interviews involved the DoH, DMCC and DAFF.  A final stakeholder consultation meeting was held to discuss the draft CC&H Plan with major stakeholders (including representatives from the aforementioned Departments) at the end of this visit.

3.  Climate change in Niue

The Pacific Climate Change Science Program (PCCSP) – a collaboration between the Niue DMCC, the Australian Bureau of Meteorology and the Commonwealth Scientific Industrial and Research Organization – reports that, over the course of the 21st century, Niue is likely to experience the following climate change phenomena (PCCSP, 2011):

- increasing temperatures;

- increasing wet season and annual rainfall;

- increasing frequency and intensity of days of extreme heat and rainfall;

- fewer cyclones (although these may be of increasing intensity);

- ocean acidification; and

- rising sea levels.

4.  Climate-sensitive health risks and adaptation options

The Tables on the following pages list a range of issues that are currently understood to represent the main threats to health from climate change in Niue, along with some strategies and activities (“adaptations”) to manage those threats.  It is important to understand that climate change will act primarily as an “amplifier” of existing health problems, rather than introducing new problems per se.

The overall risk of each climate-sensitive health issue below is based on the likelihood of an increase in the burden of each health problem (given the “climate-sensitivity” of the respective diseases) and the impact of such an increase on individuals and communities in Niue (taking into account the current burden of these diseases and the capacity of the health sector to manage them).  These assessments are inevitably somewhat subjective, and it is intended that this list of issues and adaptation strategies be reviewed and updated regularly, as circumstances change and/or new information comes to hand.

For now, there is good evidence from research performed elsewhere in the Pacific region and around the world that each of the health issues discussed below (vector-borne diseases, ciguatera, diarrhoeal disease, respiratory disease, heat-related illness, non-communicable diseases (NCD’s), health impacts of extreme weather events and skin infections/infestations) is sensitive to changes in climate (see references in Tables below).

It is also of critical importance that the particular vulnerabilities of sub-sectors of the population be recognized and that appropriate anticipatory measures be put in place to protect these individuals and groups, which include (but are not limited to):  young children, the elderly, people with disabilities, people with significant mental health issues (such as psychotic illness), outdoor workers and those in highly socially or geographically vulnerable areas (e.g. those with poor household infrastructure such as septic tanks and drainage, or those living very close to the coast).

Mental health issues may also obviously arise from climate change (e.g. extreme weather events); management of this may become a higher priority into the future.

| Key issue: Vector-borne diseases - possible increase in burden of dengue fever with warming temperatures and altered ENSO and rainfall patterns (Hales et al, 1999) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Objectives: - decrease risk and impact of dengue epidemics; avoid deaths from dengue fever |  |  |  |  |
| Strategy | Activities | Timeline | Cost | Lead agency (collaborators) |
| Control mosquito populations | Community/household measures (emptying containers) – need to emphasize community responsibility & avoid complacency Spraying, regular village inspections (could link with Village Beautification program) | Ongoing |  | DoH |
| Improve public awareness of ways to decrease risk of transmission | Health promotion messages include elimination of mosquito breeding sites and using protective measures (repellant, coils, screens, nets etc) - note community was slow to respond to health promotion messages early in recent outbreak - need to repeat health promotion messages periodically (after this outbreak subsides), e.g. before or early in wet season - get messages into schools as well as communities - consider running messages about eliminating mosquito breeding sites alongside waste management advice | Ongoing |  | DoH |
| Ensure adequate clinical capacity to manage outbreaks | Ensuring sufficient supply of test kits, fluids, analgesics etc Health professional education (updated clinical guidelines, case definitions) | Ongoing |  | DoH |
| Improve communication & coordination between clinical and environmental health teams | Regular meetings between heads of departments Sharing of information and resources (e.g. de-identified patient demographics for appropriate targeting of community control measures such as spraying) | Ongoing |  | DoH (Environment) |

| Key issue: Ciguatera (fish poisoning) - possible increase in burden of ciguatera with warming sea temperatures, changing ENSO patterns and other factors (e.g. ocean acidification, coral bleaching etc) (Llewellyn, 2010) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Objectives: - decrease risk and impact of ciguatera |  |  |  |  |
| Strategy | Activities | Timeline | Cost | Lead agency (collaborators) |
| Identify local fish species which are prone to causing ciguatera | Liaise with Fisheries and review previous studies and traditional knowledge on ciguatera in Niue - note that tourists and immigrants are higher-risk groups (as they lack traditional knowledge) | 2012-13 |  | DoH (Fisheries, ?SPC) |
| Improve public awareness of risk of ciguatera toxicity | Health promotion campaign regarding ciguatoxic fish species and lowering risk of toxicity (e.g. eating lesser amounts of smaller fish) - materials already exist (e.g. in leaflets, in Niuean) which can be updated | 2012-13 |  | DoH |
| Ensure up-to-date, evidence-based clinical management of ciguatera cases | Ongoing health professional education - note research being done in New Caledonia examining antidotes (including from local plants in Micronesia) | Ongoing |  | DoH (Medical Officers) |
| Improve communication between health and other agencies (e.g. Fisheries) | Sharing of information regarding cases/outbreaks (to ensure appropriate health promotion messages etc) | Ongoing |  | DoH, Fisheries (heads of departments) |

| Key issue: Diarrhoeal illness - possible increase in burden of diarrhoeal illness with warming temperatures and extremes of rainfall (Singh et al, 2001) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Objectives: - decrease risk and impact of diarrhoeal disease (particularly in children) |  |  |  |  |
| Strategy | Activities | Timeline | Cost | Lead agency (collaborators) |
| Improve public awareness regarding possible increased risk of diarrhoeal disease in future climate | Health promotion campaign targeting children and parents – focus on personal hygiene (e.g. “washing of hands” campaign) Educate public regarding increased risk of food contamination in warmer climate (including social and cultural practices such as feasting) | 2012-13 |  | DoH |
| Ensure safe water and food supplies | Food and water safety monitoring Testing of water supplies by Env Health staff and community water management teams - note shortfall in Env Health resources (human resources, food testing equipment etc) Provide additional training for food handlers (domestic and commercial) regarding hygiene & safe food handling/ preparation techniques | Ongoing |  | DoH, liaise with PWD/IWRM |
| Improve communication between health and other agencies (e.g. Environment, Agriculture) | Sharing of information regarding cases/outbreaks (to ensure appropriate health promotion messages etc) | Ongoing |  | DoH (Environment, Agriculture) |

| Key issue: Respiratory disease - possible increase in burden of respiratory infections (e.g. influenza, pneumonia) and obstructive airways disease (e.g. asthma) in warmer, wetter weather (Paynter et al, 2010; Hughes et al, 2011) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Objectives: - decrease risk and impact of respiratory disease (particularly in children) |  |  |  |  |
| Strategy | Activities | Timeline | Cost | Lead agency (collaborators) |
| Ensure appropriate immunization coverage | Regular influenza vaccinations for children, elderly, people with diabetes, chronic airways disease, other NCD’s - influenza vaccinations currently on voluntary basis - would be valuable to make this routine for higher-risk individuals - consider role for pneumococcal vaccinations (need to review expense) | Ongoing |  | DoH |
| Improve knowledge regarding links between environment/climate and respiratory disease | Examine health data (for seasonal patterns) and correlate with climate data if possible | Should be possible once health data available |  | DoH |

| Key issue: Heat-related illness - possible increase in dehydration, heat stress, hospitalisations and deaths during very hot days (Portier et al, 2010) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Objectives: - decrease risk and impact of heat-related illness |  |  |  |  |
| Strategy | Activities | Timeline | Cost | Lead agency (collaborators) |
| Improve public awareness regarding risks and impact of heat-related illness | Health promotion campaign targeting vulnerable groups (young children, elderly, those with co-morbid illness – particularly diabetes, cardiovascular & respiratory disease – and outdoor workers) emphasizing risk of heat stress and need for adequate hydration, cooling etc | 2012-13 |  | DoH |
| Ensure adequate cooling in households and public buildings | Consider need for distribution and/or subsidies for ventilation/cooling devices - fans, air-conditioners etc | ? |  | Government of Niue |

| Key issue: Non-communicable diseases - possible increase in burden of NCD’s due to compromised food security, decreased physical activity in warmer weather |  |  |  |  |
| --- | --- | --- | --- | --- |
| Objectives: - avoid future climate change-attributable burden of NCD’s |  |  |  |  |
| Strategy | Activities | Timeline | Cost | Lead agency (collaborators) |
| Ensure climate change considerations are incorporated into NCD programs | Link with NCD Plan | Ongoing |  | DoH |

Note:  the link between climate change and NCD’s is complex and includes both direct effects (e.g. heat stress exacerbating cardiorespiratory illnesses) and indirect effects (e.g. climate change-induced crop failure leading to compromised food security; increased ambient temperatures limiting capacity for physical activity).  An attempt has been made to represent these links visually in Figure 2 below.

Figure 2.  Link between climate change, food security and NCD’s

| Key issue: Health impacts of extreme weather events - possible increase in injuries (and deaths) and mental health problems from extreme events such as cyclones (McMichael et al, 2003) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Objectives: - ensure adequate disaster preparedness and response |  |  |  |  |
| Strategy | Activities | Timeline | Cost | Lead agency (collaborators) |
| Ensure that consideration of both health and climate change effects are incorporated into National Disaster Plan | Link with National Disaster Plan Review DoH Cyclone Plan | 2012-13 |  | DoH & National Disaster Council |
| Provide regular training in disaster response | Conduct regular briefings and/or disaster simulation training for health staff | Annually (e.g. prior to cyclone season) |  | DoH |

| Key issue: Skin infections/infestations - possible increase in skin infections/infestations with increasing temperatures and altered rainfall patterns (Ebi et al, 2006) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Objectives: - decrease risk and impact of skin infections/infestations |  |  |  |  |
| Strategy | Activities | Timeline | Cost | Lead agency (collaborators) |
| Improve public awareness regarding risk and management of skin conditions (particularly in children) | Health promotion campaign targeting parents and young children (focus on hygiene measures and elimination of scabies, bacterial, fungal & yeast infections) - materials already exist; can be re-used, refreshed, updated as required (suggest run campaigns 1-2 times/year) | 2012-13 |  | DoH |
| Prevent complications of skin infections/ infestations | Ensure prompt, appropriate treatment of skin conditions to prevent complications such as cellulitis, sepsis (particularly in children and people with diabetes) | Ongoing |  | DoH |

5.  Findings and conclusions

- Health information systems (HIS) capacity in Niue is currently very limited, with the implication that any recommendations and decisions (including those in this CC&H Plan) are made on anecdotal evidence, rather than that backed up by data

  - The Patient Information System nominally in use (MedTech32) has not been usable/accessible for several years

  - No health data, records or reports are available for review at present

  - Medical records coding is done on an ad-hoc basis by medical and nursing staff

  - Most health data and information is in written, rather than electronic format

  - No-one is currently employed in the areas of health statistics or epidemiology

  - There appears to be something of a reluctance to share health information even between health departments (e.g. medical, nursing, public health, environmental health)

- There is a substantial shortfall in resources for Environmental Health

  - This shortfall includes human resources, budget and equipment

    - These constraints limit the ability of the Environmental Health team (currently one full-time staff member and one unqualified assistant) to perform their required tasks (e.g. water and food safety monitoring) as often as they would under ideal circumstances

    - Urgent activities (such as those required during the recent dengue outbreak) have required the engagement of temporary staff and the emergency procurement of funds from outside the Environmental Health budget

  - Given that many activities related to climate change and health will fall to Environmental Health (e.g. vector-borne disease control, food and water safety), it is important that the resources of this department are strengthened

- There are many positive developments and plans with respect to long-term food and water security in Niue

  - The activities led by the DoE, DAFF and the Public Works Department, including the the Pacific Adaptation to Climate Change Project and the Integrated Water Resource Management plan, are encouraging examples of such work (e.g. provision of water tanks to all households on Niue)

- The Public and Environmental Health response (including health promotion, vector control etc) to the recent dengue fever outbreak in Niue also demonstrated impressive capacity despite the abovementioned resource constraints

  - There was however a reportedly high level of complacency on the part of the public, and a perceived reluctance from individual households and communities to carry out the mosquito control measures recommended by the DoH

    - This indicates a potential lack of understanding in the community of the seriousness of environmental health threats such as dengue fever and/or an unrealistic expectation of the capacity of the DoH to manage these issues without community assistance and participation

- It is important to recognize that the overwhelming health concern in Niue relates to the increasing burden of NCD’s

  - While climate change is likely to have an impact on NCD’s (mainly indirectly via pathways that link food, physical activity and heat – see Figure 2 above) it is encouraging to note that significant attention and resources are being directed towards managing the NCD burden in Niue.

6.  Recommendations

- The activities and strategies related to climate-sensitive health risks detailed in this CC&H Plan should be prioritized according to urgency and feasibility and included into the DoH annual workplan(s)

- This CC&H Plan should be reviewed and updated on a regular basis to incorporate new information and reflect contemporary concerns

- The Director of Health should remain the focal point for climate change and health and the lead person responsible for reviewing and implementing this Plan (unless and until another appropriate individual within DoH is nominated for this role)

- The contents of this CC&H Plan (namely the key climate-sensitive health risks and proposed adaptation strategies) should be strongly considered for inclusion in Niue’s JNAP and Second and subsequent National Communications to the UNFCCC (and future revisions of the NCCP and NHSP)

- This CC&H Plan should be used as evidence of a thorough climate change and health vulnerability and adaptation assessment when approaching donors and other agencies for funding and technical support (for health system strengthening and/or climate change adaptation)

- Prompt consideration should be given to the respective costs and feasibility of the activities outlined above as this CC&H Plan moves towards endorsement and implementation

- Improving HIS capacity is an overarching priority for the DoH

  - Improved collection, coding, storage and analysis of health data is imperative for appropriate strategic planning for the health sector

  - This measure will necessarily include training of staff in health data management

  - The burden of health problems in Niue should be reviewed and quantified as precisely as possible as a matter of priority (note the recent completion of the NCD “STEPS” survey), in order to better inform health policy planning

- Education, awareness-raising and health promotion activities are key in improving the resilience of individuals and communities in Niue to the health impacts of climate change

  - Health promotion activities aimed at reducing the risk of dengue fever (e.g. elimination of mosquito breeding sites; personal and household protective measures against mosquito bites), diarrhoeal disease (hygiene, sanitation, food storage and handling) and ciguatera (identifying high-risk fish species and fishing practices) would be relatively easy and cheap to implement in the short term

  - School education campaigns and curriculum learning areas related to climate change should be reviewed and updated (if necessary) to include consideration of health impacts (link with PACC project activities with Department of Education)

- Improved communication and collaboration between agencies (e.g. DoH and DAFF in areas of food security, nutrition and ciguatera; DoH and DoE in community environmental health) should be prioritized in order to streamline activities, share information and resources and avoid duplication

- Future research activities

  - Correlation of health with climate data (in the future, when sufficient health data is available) would be a useful exercise in determining local relationships between climatic factors (such as temperature and rainfall) and health outcomes (e.g. respiratory infections, exacerbations of asthma and episodes of diarrhoeal disease in young children).

References

Ebi KL, Lewis ND, Corvalan C.  Climate variability and change and their potential health effects in small island states: information for adaptation planning in the health sector. Environ Health Perspect 2006; 114(12): 1957-1963

Hales S, Weinstein P, Souares Y, Woodward A.  El Niño and the dynamics of vectorborne disease transmission.  Environ Health Perspect 1999; 107(2): 99-102

Hughes L, McMichael A.  The Critical Decade: Climate change and Health.  Australian Department of Climate Change and Energy Efficiency, Canberra, 2011

Llewellyn LE.  Revisiting the association between sea surface temperature and the epidemiology of fish poisoning in the South Pacific: reassessing the link between ciguatera and climate change.  Toxicon 2010; 56(5): 691-697

McMichael AJ, Campbell-Lendrum DH, Corvalan CF et al (Editors).  Climate change and human health: risks and responses.  WHO, Geneva, 2003; pg 90-95

Paynter S, Ware R, Weinstein P et al.  Childhood pneumonia: a neglected, climate-sensitive disease?  Lancet 2010; 376: 1804-1805

Portier CJ, Thigpen TK, Carter SR et al.  A human health perspective on climate change: a report outlining the research needs on the human health effects of climate change.  Environ Health Perspect April 2010; pg 29-31

Singh RB, Hales S, de Wet N et al.  The influence of climate variation and change on diarrheal disease in the Pacific islands.  Environ Health Perspect 2001; 109: 155-159

Appendix.

Table 1.  Key climate-sensitive health issues discussed in Phase One

Table 2.  Phase One plan for CC&H activities

Table 3.  Main health issues in Niue identified from Phase Two stakeholder meeting

- Rising numbers / prevalence of NCD’s (diabetes, hypertension, gout)

- Rising prevalence of obesity/overweight

- Communicable diseases

  - Skin infections/cellulitis in adults and children particularly over warmer/humid months

  - Respiratory tract infections particularly over the colder months

  - Food poisoning and diarrhoeal diseases

- Injuries – most commonly related to simple household accidents

- Increasing numbers of fish poisoning

- Tobacco  smoking including young people

- Excess Alcohol consumption

- Mental health – depression, anxiety, stress

Table 4.  List of key points from Phase Two community consultations

- Natural disasters is a major concern for Niue.

- The issue of evacuation of houses evacuation of houses in low lying coastal areas.

- Tsunami alert came about with the case of Japan people headed up to houses in land.

- Fish poisoning a major concern they need to have things in place for testing fish and identifying key issues around fish poisoning.

- The need for first aid kits in the village so people in the village can access these kits.

- The use of traditional healing in case the hospital has problems with medication not being available or very difficult to get to hospital.

- The inclusion of long drops being brought back to for accessing of toilets.

- Need to have a person who is responsible for medical care in each village.